## Slide 1
Iowa Total Care Meeting In The Community
Sept 17, 2024
Iowa Medicaid
Provider Townhall
December 18, 2025
Confidential and Proprietary Information

## Slide 2
LTSS Project Overview
Increase number of LTSS Providers in our network
Educate Providers about LTSS services and their eligibility to provide them
Collaborate with MCOs to survey Providers
  Tailor educational content to their needs
  Capture Provider feedback and work to remove barriers to providing services and/or expanding services within existing geographic footprint
Survey members and Community Based Case Managers (CBCMs) to capture feedback, work to increase utilization of LTSS services
Education presented to all current LTSS CBCM and embedded into new employee education
Primary Departments Impacted:
  Network Development & Contracting
  LTSS
Data & Analytics
Provider Engagement
Other departments as needed

## Slide 3
Contracting Plan
Outreach has been successful in engaging providers
4 new contracts in process
Education Plan
Comprehensive training decks created (new/existing providers)
68 staff trained through live sessions, with monthly internal trainings ongoing
Provider Engagement workgroup established to align messaging across teams
MCO collaboration in progress on statewide provider survey
Presented at multiple in-person Provider Forums and Summits
Internal partnerships launching drop-ins and ride-alongs
Ongoing provider webinars and post-summit outreach
Barrier Identification and Reduction Plan
5-day TAT on authorizations for new and current waiver members (compared to 7-day requirement)
Limited data to analyze performance opportunities, education, etc.
Survey materials with MCO branding in development; HHS approval to follow.
Not all Providers know they are eligible to provide LTSS services
  We address this barrier with our Education Plan.
    Provider and Member benefit and eligibility talking points
    Board meetings
    LTSS Stakeholder Advisory Board
    Providing education at site visits
  We established a single point of contact for Provider inquiries through our state-wide Provider Engagement Account Managers
    We continue to maintain a no wrong door policy
Successes
Barriers
Successes & Barriers

## Slide 4
B3 Services Project Overview
Increase number of B3 Providers in our network
Educate Providers about B3 services and their eligibility to provide them
Collaborate with MCOs to survey Providers
  Tailor educational content to their needs
  Capture Provider feedback and work to remove barriers to providing services and/or expanding services within existing geographic footprint
Decrease involuntary discharges and hospitalizations post B3
Primary Departments Impacted:
  Network Development & Contracting
  Behavioral Health
Provider Engagement
Data & Analytics
LTSS
Other depts as needed

## Slide 5
Contracting Plan
Collaborated with Provider Engagement department to educate a provider on how to get certified and enrolled for Peer Support services
Provider Summits resulted in 4 new providers
Education Plan
Comprehensive training decks created (new/existing providers)
68 staff trained through live sessions, with monthly internal trainings ongoing
Provider Engagement workgroup established to align messaging across teams
MCO collaboration in progress on statewide provider survey
Presented at multiple in-person Provider Forums and Summits
Targeted internal partnerships launching drop-ins and ride-alongs
Ongoing provider webinars and post-summit outreach
Not all Providers know they are eligible to deliver B3 services.
  We address this barrier with our Education Plan.
    Provider and Member benefit and eligibility talking points
    Board meetings
    Providing education at site visits
  We established a single point of contact for provider inquiries through our state-wide Provider Engagement Account Managers
    We continue to maintain a no wrong door policy
Proactively identifying B3 Providers, we are currently engaging known B3 Providers.
We are outreaching to the other MCOs to identify approaches to identify these Providers proactively
Lack of prescription of services
Providers concerned about risk and payback and apply services appropriately
Successes
Barriers
Successes & Barriers

## Slide 6: Building Workforce Solutions for Iowa
Iowa Total Care Workforce Scholarships Summary
Direct Service Professional (DSP) Certification Program
Community Health Worker Scholarships
Family and Peer Support Specialists
Behavioral Health Certification Program
In 2023, Iowa Total Care partnered with Des Moines Area Community College (DMACC) to offer DSP Program scholarships.
Iowa Total Care is partnering with DMACC to support the Community Health Worker Program and provide scholarships.
To expand access to Family and Peer Support Specialists, we will offer scholarships for individuals to complete this certification from the Iowa Peer Workforce Collaborative.
This program provides enhanced education for individuals who may be new to or currently working in the behavioral health field, including a field-based internship with Clive Behavioral Health.
120 scholarships available per year
100 scholarships available per year
150 scholarships available per year
50 scholarships available per year
Scholarship Type
Description
Scholarships Available
Total: 420 scholarships