## Sheet1
Safe Kids Portfolio
| Project |  | 2025-11-24 | 2025-12-24 |  | 2025-01-25 | 2025-02-25 |  | 2025-03-25 | 2025-04-25 |  | 2025-05-25 | 2025-06-25 | 2025-07-25 |  | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27
| Marketing and |  | Discovery |  |  | Planning |  |  |  | Execution |  |  |  | Transition
Recruitment Plan
Integrated CCWIS | Process Mapping |  | Execution
| RFI Development |  |  |  |  | Discovery | Planning |  |  | Execution
| Product Procurement | [11 empty] | Planning |  | Execution
| Product Configuration | [19 empty] | Execution
Right Seat Analysis | Social Work Journeyman |  | Planning | [8 empty] | Execution
| (S) Embedded SW |  | Discovery | Plan | Execution | [7 empty] | Transition
Associate Expansion
| START Implementation |  | Discovery | Planning | [7 empty] | Execution |  |  |  | Transition
| Family Finding Specialist (HF1003) | [8 empty] | Planning |  |  | Execution | [6 empty] | Transition
| Statewide Data Maps |  |  |  |  | Discovery | [5 empty] | Planning |  |  |  |  | Execution
| (S) Bilingual Worker Compensation | [10 empty] | Planning | Execution | [11 empty] | Transition
| Central Consult Model |  |  |  |  | Planning |  |  | Execution | [7 empty] | Transition
Leadership Empowerment | *Other Projects TBD
Safe Kids Portfolio
| Project |  | 2025-11-24 | 2025-12-24 |  | 2025-01-25 | 2025-02-25 |  | 2025-03-25 | 2025-04-25 |  | 2025-05-25 | 2025-06-25 | 2025-07-25 |  | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27
| Family Centered Services Contract Redesign |  | Discovery |  |  |  | Planning |  |  | Execution |  |  |  | Transition
| Medical Consultation | [10 empty] | Discovery |  |  |  | Planning |  |  | Execution |  |  |  | Transition
Model
| Healthcare and Medication Oversight | [8 empty] | Discovery |  |  |  | Planning | [5 empty] | Execution
| Drug Testing Redesign |  | Planning | [5 empty] | Execution
| Foster Care Licensing Standards Redesign | [11 empty] | Discovery |  |  |  |  | Planning |  |  | Execution or Delayed Execution
|  | Foster Care Pre-Service Training | [10 empty] | Discovery |  |  |  | Planning |  | Execution
| Safety, Security, and Quality for QRTPs | [5 empty] | Planning |  |  |  | Execution | [7 empty] | Transition
|  | Complex Case Review Redesign | [11 empty] | Discovery |  |  | Planning |  |  | Execution |  |  |  | Transition
Ending Group Care | Therapeutic Foster Care Expansion |  | Planning | [9 empty] | Execution | [6 empty] | Transition
| Treatment Foster Care | [16 empty] | Discovery |  |  |  | Planning | [7 empty] | Execution
| Communications plan for CPS Division (In) |  | Planning |  | Execution
| Communications plan for CPS stakeholders (Out) |  |  |  |  | Planning |  | Execution
*Business Process Change Initiatives TBD
|  | Report Dissemination | Discovery |  |  | Planning | [6 empty] | Execution
Process Change
|  | (S) Critical Incident Reporting |  |  |  | Discovery | Planning |  |  | Execution