## Perf Report
Iowa Core Standardized Assessments for Home and Community-Based Services
Telligen Contract # MED-20-004
Monthly Performance Reporting Tool
Reporting Period: December 2025
Business Area | Contract Reference | Performance Standard/Deliverable | Due Date/Deadline | Result Definition | Actual timliness Results | Reasons for untimeliness See Exceptions to 95% Report for Details | Telligen timeliness | Reasons for untimeliness | Standard Met 95% Y/N
Assessments | 1.3.2.C.1, 1.3.2.C.1.b 1.3.2.C.1.c 1.3.2.C.1.d, 1.3.2.C.2, 1.3.2.C.3 | Conduct and submit face-to-face and telephonic assessments for persons newly entering services and persons that have been previously assessed entering services, QA review may not have been completed by end of month | As identified in contract | Total # of timely assessments/ Total # assessments | 2003/4298 | * 25 Late response from member * 8 Member in Hopsital/SNF * 18 Member/CM/Provider request * 63 rescheduled due to member or CM * 2 Unable to reach member * 0 Waiting on Full Scale IQ * 4 Other: - MCO - not on CSR report * 2175 Telligen responsibility | 2123/4298 | * Delayed scheduling due to volume * First availability on calendars due to volume * Rescheduled due to Telligen | N (49.4%)
Business Area | Contract Reference | Performance Standard/Deliverable | Due Date/Deadline | Result Definition | Result | Standard Met 95% Y/N | Notes
Assessments | 1.3.2.C.4 | Upload assessments to IMPA, all assessments have been through QA and are billable | Within 5 b days from assessment completion date | Total # assessments uploaded within 5 days/Total assessments uploaded | 4222/4298 | Y (98.2%)
General | 1.3.2.A.1 | Respond to email or telephone inquiries from members, authorized reps, providers and/or facilities | Within two business days of receipt | Total responses within 2 b days/Total # of responses to email/telephone inquires | Voicemail: 144/145 = 99.31% Email: 626/626 =100% | Y (99.87%)
Business Area | Contract Reference | Reporting due during month | Due Date/Time | Result Definition | Result | Standard Met Y/N | Notes
General | 1.3.1.1.F | Provide subject matter expertise | As identified | Date requested | Ongoing | Y
General | 1.3.1.1.C.2 | Ongoing Member and stakeholder feedback | Ongoing | Likert scale scoring of survey responses | 4.58/5 | Y
General | 1.3.1.1.D.3 | Notify Agency of problems/ concerns | 2 b day of discovery | Total notifications within 2 b days of discovery/Total # of discoveries | 0/0 | Y
General | 1.3.1.2.B.2 | Submit SOP changes to the Agency | Within 30 c days of the change | N/A | N/A | Y
General | 1.3.1.2.B.3 | Update SOPs annually | Annually, due October 1 | Date requested | 2025-09-04 | Y
General | 1.3.2.A.2 | Participate in 100% of assigned appeal hearing | Upon request | Total # of hearings participated/ Total # hearings | No appeal requests this month | Y
Inter-rater Reliability | 1.3.2.D.1 | Achieve 85% IRQR on SIS interview scores | Each assessor is measured annually. Completed IRQR scores reported each month | Assessor receives score of greater than, less than or equal to 85% | N/A | Y | N/A - SIS is no longer completed in Iowa
Inter-rater Reliability | 1.3.2.D.2 | Achieve 80% IRR on interRAI scores | Each assessor is measured annually, due July 31, 2026 | Assessor receives score of greater than or equal to 80% | 42/42 | Y
Quality Assurance | 1.3.2.E | Meet reliability and quality standards for specific CSA | Monthly | Scoring | 3409/3744 | Y (91%) | * This score is based on errors discovered in assessments in our internal QA process. Therefore, they were corrected prior to submission to the State and the Reliability and quality standards were met on the finalized assessment. This process is described in our CSA Quarterly report of QA activities.
Contract | 1.3.1.1.G.1.f | Submit SOC2 Compliance documentation and Vendor Questionnaire | Annually | Date requested | 2025-10-01 | Y
Contract | 1.3.2.H | Attend all Agency meetings | As identified | 2020-03-31 | Attended | Y
Business Area | Contract Reference | Reporting due during month | Due Date/Time | Result Definition | Accepted by Agency (Y/N) | Standard Met Y/N
Reporting | 1.3.2.F | Submit Monthly Performance Report | 15th c day of the following month | 2026-01-15 | Completed | Y
Reporting | 1.3.1.6.B.4 | MCO Ride-Along and Quality Oversight Report | 15th c day of the following month | 2026-01-15 | Completed | Y

## Sheet1
4.6538
4.7037
4.7407
4.6667
4.4815
4.6296
4.4444
4.8519
4.6465